## Sheet1
Activity Log Book
Sr. No. | Student SAPID | Student Name | Supervisor | Date | Weekly progress |  | Target for next week
[5 empty] | Individual Contribution | Work done in this week
1 | 60004220126 | Shashwat Shah | Prof. Ruhina Karani | 2025-02-11 | Factory Survey Done | Coordinated for industrial pipeline survey as per ma’am’s input | successfully test all the major components
2 | 60004210147 | Khushi Jobanputra | Prof. Ruhina Karani | 2025-02-11 | Factory Survey Done |  | successfully test all the major components
3 | 60004210122 | Kruti Shah | Prof. Ruhina Karani | 2025-02-11 | Factory Survey Done |  | successfully test all the major components
4 | 60004210235 | Manasvi Gupta | Prof. Ruhina Karani | 2025-02-11 | Factory Survey Done |  | successfully test all the major components
5
6 | 60004220126 | Shashwat Shah | Prof. Ruhina Karani | 2025-02-25 | Testing all the components | Successfully tested all major components: MQ5, MQ135, DHT11, Distance Sensor, Torch, Camera, GPS module | Motor testing and Twilio SMS setup
7 | 60004210147 | Khushi Jobanputra | Prof. Ruhina Karani | 2025-02-25 | Testing all the components |  | Motor testing and Twilio SMS setup
8 | 60004210122 | Kruti Shah | Prof. Ruhina Karani | 2025-02-25 | Testing all the components |  | Motor testing and Twilio SMS setup
9 | 60004210235 | Manasvi Gupta | Prof. Ruhina Karani | 2025-02-28 | Testing all the components |  | Motor testing and Twilio SMS setup
10
12 | 60004220126 | Shashwat Shah | Prof. Ruhina Karani | 2025-03-11 | Hardware-software sync + Twilio alerts | Completed motor testing, Twilio SMS setup, and ensured Firebase communication | Finalize AutoCAD design
13 | 60004210147 | Khushi Jobanputra | Prof. Ruhina Karani | 2025-03-11 | Hardware-software sync + Twilio alerts |  | Finalize AutoCAD design
14 | 60004210122 | Kruti Shah | Prof. Ruhina Karani | 2025-03-11 | Hardware-software sync + Twilio alerts |  | Finalize AutoCAD design
15 | 60004210235 | Manasvi Gupta | Prof. Ruhina Karani | 2025-03-11 | Hardware-software sync + Twilio alerts |  | Finalize AutoCAD design
16
17 | 60004220126 | Shashwat Shah | Prof. Ruhina Karani | 2025-04-08 | CAD design | Completed AutoCAD views (front, rear, top, bottom, side). | Testing of magnets and new motors
18 | 60004210147 | Khushi Jobanputra | Prof. Ruhina Karani | 2025-04-08 | CAD design |  | Testing of magnets and new motors
19 | 60004210122 | Kruti Shah | Prof. Ruhina Karani | 2025-04-08 | CAD design |  | Testing of magnets and new motors
20 | 60004210235 | Manasvi Gupta | Prof. Ruhina Karani | 2025-04-08 | CAD design |  | Testing of magnets and new motors
21
22 | 60004220126 | Shashwat Shah | Prof. Ruhina Karani | 2025-04-15 | Magnets and motor testing | Completed testing of magnetic grip and motor performance on vertical & curved metallic pipe surfaces | Documentation of Patent to be Finished
23 | 60004210147 | Khushi Jobanputra | Prof. Ruhina Karani | 2025-04-15 | Magnets and motor testing |  | Documentation of Patent to be Finished
24 | 60004210122 | Kruti Shah | Prof. Ruhina Karani | 2025-04-15 | Magnets and motor testing |  | Documentation of Patent to be Finished
25 | 60004210235 | Manasvi Gupta | Prof. Ruhina Karani | 2025-04-15 | Magnets and motor testing |  | Documentation of Patent to be Finished
26
27 | 60004220126 | Shashwat Shah | Prof. Ruhina Karani | 2025-04-22 | Working on utility patent documents | Worked on preparing design patent documentation, diagrams, and description drafts | Testing Robot for grip on pipes
28 | 60004210147 | Khushi Jobanputra | Prof. Ruhina Karani | 2025-04-22 | Working on utility patent documents |  | Testing Robot for grip on pipes
29 | 60004210122 | Kruti Shah | Prof. Ruhina Karani | 2025-04-22 | Working on design patent documents |  | Testing Robot for grip on pipes
30 | 60004210235 | Manasvi Gupta | Prof. Ruhina Karani | 2025-04-22 | Working on design patent documents |  | Testing Robot for grip on pipes
31
32 | 60004220126 | Shashwat Shah | Prof. Ruhina Karani | 2025-04-29 | Testing robot on pipe | Conducted robot testing on actual metallic pipes — verified grip, motion, and sensor accuracy | Finish Black Book Making
33 | 60004210147 | Khushi Jobanputra | Prof. Ruhina Karani | 2025-04-29 | Testing robot on pipe |  | Finish Black Book Making
34 | 60004210122 | Kruti Shah | Prof. Ruhina Karani | 2025-04-29 | Testing robot on pipe |  | Finish Black Book Making
35 | 60004210235 | Manasvi Gupta | Prof. Ruhina Karani | 2025-04-29 | Testing robot on pipe |  | Finish Black Book Making
36
37 | 60004220126 | Shashwat Shah | Prof. Ruhina Karani | 2025-05-04 | Blackbook making | BlackBook making | Final Sumbission
38 | 60004210147 | Khushi Jobanputra | Prof. Ruhina Karani | 2025-05-04 | Blackbook making |  | Final Sumbission
39 | 60004210122 | Kruti Shah | Prof. Ruhina Karani | 2025-05-04 | Blackbook making |  | Final Sumbission
40 | 60004210235 | Manasvi Gupta | Prof. Ruhina Karani | 2025-05-04 | Blackbook making |  | Final Sumbission