## Slide 1: Module 4
Planning Projects

## Slide 2: Contents
Crashing project time
Resource loading and levelling
Goldratt's critical chain
Project Stakeholders and Communication plan
Risk Management in projects: Risk management planning, Risk identification and risk register, Qualitative and quantitative risk assessment, Probability and impact matrix. Risk response strategies for positive and negative risks

## Slide 3: Crashing project time
Project Cost
Direct Cost
Indirect Cost
Crash time is the minimum activity duration to which an activity can be compressed by increasing the resources and hence by increasing the direct cost.

## Slide 4: Slope Approximation

## Slide 6
Direct Cost
This cost is directly dependent upon the amount of resources involved in the execution of the individual activities. This is the cost of the materials, equipment and labour required to perform the activity. If the activity is performed by a subcontractor, the price of the subcontract will be the activity direct cost.
The activity duration can be varied by varying the cost. Point N, ‘normal point’ corresponds to the normal activity time. If the duration is further increased, the decrease in cost is insignificant, as the activity is compressed, the direct cost goes on increasing. If it is compressed beyond C, the cost increases very rapidly for insignificant change in the activity duration. This point is called ‘crash point’.

## Slide 7
Indirect Cost
Project indirect cost can further be sub-divided into two parts: fixed indirect cost and variable indirect cost.
The fixed indirect cost is due to the general and administrative expenses, licence fee, insurance cost and taxes and does not depend upon the progress of the project.
The variable indirect cost depends upon the time consumed by the project and consists of overhead expenditure, supervision, interest on capital and depreciation, penalty for delays (if any), etc.
It is assumed that the indirect cost increases linearly with time.

## Slide 9: Crashing the Network

## Slide 15: All activities fully crashed

## Slide 17: Resource loading and levelling
Assumption of sufficient resources in PERT , CPM.
Cumulative demand of resource.
Demand fluctuates from very high at one time to a very low at another time.
Fluctuation affects total project cost due to high idle times.
To reduce idle period, resources on non-critical paths are to be shifted by using their floats.
This makes the demand of resources as uniform as possible.
Objective of resource scheduling is to bring down the costs & reduce pressure on the limited resources in conflicting demands.

## Slide 18: Types of Resource Scheduling
Depending upon the constraints they may be of two types:
  Resource Smoothing- Constraint is the project duration. Demand on resource is made as uniform as possible. The start times of the activities on the non-critical paths are shifted, while the project duration remains unchanged. This type of resource scheduling is known as Resource Smoothing.
  Resource Levelling – Constraint is the availability of certain resources. Project duration may be extended. But demand of certain resources should not go beyond the specified level. This type of resource scheduling is known as Resource Levelling.

## Slide 22
Types of Resource Levelling
Variable Resource Levelling
Fixed Resource Levelling
Combined Resource Levelling.

## Slide 23: Goldratt's critical chain
In practice, project managers carefully manage slack on sensitive resource-limited projects.
Eliyahu Goldratt, who championed the “theory of constraints” in his popular book The Goal, advocates an alternative approach to managing slack.
He has coined the term “critical-chain” to recognize that the project network may be constrained by both resource and technical dependencies.
Each type of constraint can create task dependencies, and in the case of resource constraints, new task dependencies can be created!

## Slide 24
The critical chain refers to the longest string of dependencies that exist on the project.
Chain is used instead of path, since the latter tends to be associated with just technical dependencies not resource dependencies.
Goldratt uses the critical chain concept to develop strategies for accelerating the completion of projects. These strategies are based on his observations about time estimates of individual activities.

## Slide 25: Time Estimates
The median time (50/50 chance) is overestimated by approximately 30 to 40 percent

## Slide 26
Why, if there is a tendency to overestimate activity durations, and add safety to the end of a project, do so many projects come in behind schedule?
Critical-Chain Project Management (CCPM) offers several explanations:
Parkinson’s law
Self-protection
Dropped baton
Excessive multitasking
Resource bottlenecks
Student syndrome (procrastination)

## Slide 27
CCPM recommends inserting time buffers into the schedule to act as “shock absorbers” to protect the project completion date against task durations taking longer than the 50/50 estimate.
There are three kinds of buffers in CCPM:
Project Buffer
Feeder Buffers
Resource Buffers
All buffers reduce the risk of the project duration being late and increase the
chance of early project completion.

## Slide 28: Project Stakeholders and Communication plan
Project Communications Management includes the processes necessary to ensure that the information needs of the project and its stakeholders are met through development of artifacts and implementation of activities designed to achieve effective information exchange.
Project Communications Management consists of two parts. The first part is developing a strategy to ensure communication is effective for stakeholders. The second part is carrying out the activities necessary to implement the communication strategy.
The Project Communications Management processes are:
  Plan Communications Management—The process of developing an appropriate approach and plan for project communication activities based on the information needs of each stakeholder or group, available organizational assets, and the needs of the project.
  Manage Communications—The process of ensuring timely and appropriate collection, creation, distribution, storage, retrieval, management, monitoring, and the ultimate disposition of project information.
  Monitor Communications—The process of ensuring the information needs of the project and its stakeholders are met.

## Slide 31
Steps to Develop the Communication Plan

## Slide 32: Risk Management In Projects
Project Risk Management includes the processes of conducting risk management planning, identification, analysis, response planning, response implementation, and monitoring risk on a project.
The objectives of project risk management are to increase the probability and/or impact of positive risks and to decrease the probability and/or impact of negative risks, in order to optimize the chances of project success.

## Slide 33
The Project Risk Management processes as described by PMBOK are:
  Plan Risk Management—The process of defining how to conduct risk management activities fora project.
  Identify Risks—The process of identifying individual project risks as well as sources of overall project risk, and documenting their characteristics.
  Perform Qualitative Risk Analysis—The process of prioritizing individual project risks for further analysis or action by assessing their probability of occurrence and impact as well as othercharacteristics.
  Perform Quantitative Risk Analysis—The process of numerically analyzing the combined effect of identified individual project risks and other sources of uncertainty on overall project objectives.
  Plan Risk Responses—The process of developing options, selecting strategies, and agreeing on actions to address overall project risk exposure, as well as to treat individual project risks.
  Implement Risk Responses—The process of implementing agreed-upon risk response plans.
  Monitor Risks—The process of monitoring the implementation of agreed-upon risk response plans, tracking identified risks, identifying and analyzing new risks, and evaluating risk process effectiveness throughout the project.

## Slide 36
Step 1: Risk Identification

## Slide 39
Step 2: Risk Assessment

## Slide 41
(high impact/high likelihood),
(low impact/low likelihood).

## Slide 42
Step 3: Risk Response Development - When a risk event is identified and assessed, a decision must be made concerning which response is appropriate for the specific event. Responses to risk can be classified as mitigating, avoiding, transferring, sharing, or retaining.

## Slide 43
Step 4: Risk Response Control
Typically the results of the first three steps of the risk management process are summarized in a formal document often called the risk register.
A risk register details all identified risks, including descriptions, category, and probability of occurring, impact, responses, contingency plans, owners, and current status. The register is the backbone for the last step in the risk management process: risk control. Risk control involves executing the risk response strategy, monitoring triggering events, initiating contingency plans, and watching for new risks. Establishing a change management system to deal with events that require formal changes in the scope, budget, and/or schedule of the project is an essential element of risk control.
Project managers need to monitor risks just like they track project progress.
Risk assessment and updating needs to be part of every status meeting and progress report system.