## Slide 1: Module 5
5.1 Executing Projects
5.2 Monitoring and Controlling Projects
5.3 Project Contracting

## Slide 2: Contents
5.1 Executing Projects
5.2 Monitoring and Controlling Projects:
Planning, monitoring and controlling cycle,
Information needs and reporting, engaging with all stakeholders of the projects,
Team management, communication and project meetings
Earned Value Management techniques for measuring value of work completed;
Using milestones for measurement; change requests and scope creep,
Project audit
5.3 Project Contracting
Project procurement management
contracting and outsourcing

## Slide 3
The Executing Process Group consists of those processes performed to complete the work defined in the project management plan to satisfy the project requirements.
This Process Group involves coordinating resources, managing stakeholder engagement, and integrating and performing the activities of the project in accordance with the project management plan.
5.1 Executing Projects

## Slide 4
DIRECT AND MANAGE PROJECT WORK- It is the process of leading and performing the work defined in the project management plan and implementing approved changes to achieve the project's objectives.
The key benefit of this process is that it provides overall management of the project work and deliverables, thus improving the probability of project success.

## Slide 5
MANAGE PROJECT KNOWLEDGE: It is the process of using existing knowledge and creating new knowledge to achieve the project's objectives and contribute to organizational learning.
The key benefits of this process are that prior organizational knowledge is leveraged to produce or improve the project outcomes and that knowledge created by the project is available to support organizational operations and future projects or phases. This process is performed throughout the project.

## Slide 6
MANAGE QUALITY: Manage Quality is the process of translating the quality management plan into executable quality activities that incorporate the organization's quality policies into the project.
The key benefit of this process is that it increases the probability of meeting the quality objectives, as well as identifying ineffective processes and causes of poor quality. This process is performed throughout the project.

## Slide 7
ACQUIRE RESOURCES: It is the process of obtaining team members, facilities, equipment, materials, supplies, and other resources necessary to complete project work.
The key benefit of this process is that it outlines and guides the selection of resources and assigns them to their respective activities. This process is performed periodically throughout the project as needed.

## Slide 8
DEVELOP TEAM: It is the process of improving competencies, team member interaction, and overall team environment to enhance project performance.
The key benefit of this process is that it results in improved teamwork, enhanced interpersonal skills and competencies, motivated employees, reduced attrition, and improved overall project performance. This process is performed throughout the project.

## Slide 9
MANAGE TEAM: It is the process of tracking team member performance, providing feedback, resolving issues, and managing team changes to optimize project performance.
The key benefit of this process is that it influences team behavior, manages conflict, and resolves issues.

## Slide 10
MANAGE COMMUNICATIONS: It is the process of ensuring timely and appropriate collection, creation, distribution, storage, retrieval, management, monitoring, and the ultimate disposition of project information.
The key benefit of this process is that it enables an efficient and effective information flow between the project team and the stakeholders. This process is performed throughout the project.

## Slide 11
IMPLEMENT RISK RESPONSES: It is the process of implementing agreed-upon risk response plans.
The key benefit of this process is that it ensures that agreed-upon risk responses are executed as planned in order to address overall project risk exposure, as well as to minimize individual project threats and maximize individual project opportunities. This process is performed throughout the project.

## Slide 12
CONDUCT PROCUREMENTS: It is the process of obtaining seller responses, selecting a seller, and awarding a contract.
The key benefit of this process is that it selects a qualified seller and implements the legal agreement for delivery. This process is performed periodically throughout the project as needed.

## Slide 13
MANAGE STAKEHOLDER ENGAGEMENT: It is the process of communicating and working with stakeholders to meet their needs and expectations, address issues, and foster appropriate stakeholder involvement.
The key benefit of this process is that it allows the project manager to increase support and minimize resistance from stakeholders. This process is performed throughout the project.

## Slide 14: 5.2 Monitoring and Controlling Projects
The Monitoring and Controlling Process Group consists of those processes required to track, review, and regulate the progress and performance of the project.
Monitoring is collecting project performance data, producing performance measures, and reporting and disseminating performance information.
Controlling is comparing actual performance with planned performance, analyzing variances, assessing trends to effect process improvements, evaluating possible alternatives, and recommending appropriate corrective action as needed.

## Slide 15
MONITOR AND CONTROL PROJECT WORK: It is the process of tracking, reviewing, and reporting the overall progress to meet the performance objectives defined in the project management plan.
The key benefit of this process is that it allows stakeholders to understand the current state of the project, to recognize the actions taken to address any performance issues, and to have visibility into the future project status with cost and schedule forecasts. This process is performed throughout the project.

## Slide 16: Earned Value Management techniques for measuring value of work completed
The monitoring of performance for the entire project is very crucial.
Individual task performance must be monitored carefully because the timing and coordination between individual tasks is important. But overall project performance is the crux of the matter and must not be overlooked.
One way of measuring overall performance is by using an aggregate performance measure called earned value.
Estimating the “percent completion” of each task (or work package) is very important.

## Slide 17
There are several conventions used to aid in estimating percent completion:
• The 50–50 rule
• The 0–100 percent rule.
• Critical input use rule
• The proportionality rule.
The Earned Value Chart
The earned value chart provides a basis for evaluating cost and performance to date.

## Slide 19
We identify several variances on the earned value chart following two primary guidelines:
A negative variance is “bad,” and
the cost and schedule variances are calculated as the earned value minus some other measure.
The cost (or sometimes the spending) variance (CV) is the difference between the amount of money we budgeted for the work that has been performed to date, that is, the earned value, EV, and the actual cost of that work (AC).
EV - AC = cost variance (CV, overrun is negative)
The schedule variance (SV) is the difference between the EV and the cost of the work we scheduled to be performed to date, or the planned value (PV).
EV - PV = schedule variance (SV, behind is negative)
The time variance is the difference in the time scheduled for the work that has been performed (ST) and the actual time used to perform it (AT).
ST - AT = time variance (TV, delay is negative)

## Slide 20
The variances are also often formulated as ratios rather than differences so that the cost variance becomes the Cost Performance Index (CPI) = EV/AC, the schedule variance becomes the Schedule Performance Index (SPI) = EV/PV, and the time variance becomes the Time Performance Index (TPI) = ST/AT.
Use of ratios is particularly helpful when an organization wishes to compare the performance of several projects (or project managers), or the same project over different time periods.
Also, the two indexes, CPI and SPI, are combined to make a type of “critical ratio” called the Cost–Schedule Index
The estimated cost to complete (ETC) is defined as ETC = (BAC - EV) /CPI
The estimated cost at completion (EAC) is defined as EAC = (ETC+ AC)

## Slide 21
Example 1
Assume that operations on a work package were expected to cost $1,500 to complete the package. They were originally scheduled to have been finished today. At this point, however, we have actually expended $1,350, and we estimate that we have completed two-thirds of the work. What are the cost and schedule variances?

## Slide 22
Solution:

## Slide 23
A software development project at day 70 exhibits an actual cost of $78,000 and a scheduled cost of $84,000. The software manager estimates a value completed of $81,000. What are the cost and schedule variances and CSI? Estimate the time variance.

## Slide 24
Using milestones for measurement
Figure shown below is a summary milestone report. Each project has a series of steps that must be completed. Each has an original schedule that may be amended for use as a current schedule. Steps are completed in actual times. This form helps program managers coordinate several projects by trying to schedule the various steps to minimize the degree to which the projects interfere with one another by being scheduled for the same facilities at the same time.

## Slide 25: Project Control
Control is the last element in the implementation cycle of planning-monitoring-controlling
Control is focused on three elements of a project
  Performance
  Cost
  Time
Chapter 11-1
Notes: In essence, control is the act of reducing the difference between plan and reality. The PM is constantly concerned with these three aspects of the project. Is the
project delivering what it promised to deliver or more? Is it making delivery at or below
the promised cost? Is it making delivery at or before the promised time? It is strangely easy to
lose sight of these fundamental targets, especially in large projects with a wealth of detail and a
great number of subprojects. Large projects develop their own momentum and tend to get out of
hand, going their own way independent of the wishes of the PM and the intent of the proposal.

## Slide 26: Controlling Performance
There are several things that can cause a project’s performance to require control:
  Unexpected technical problems arise
  Insufficient resources are available when needed
  Insurmountable technical difficulties are present
  Quality or reliability problems occur
  Client requires changes in specifications
  Inte rfunctional complications arise
  Technological breakthroughs affect the project
Chapter 11-2

## Slide 27: Controlling Cost
There are several things that can cause a project’s cost to require control:
  Technical difficulties require more resources
  The scope of the work increase
  Initial bids were too low
  Reporting was poor or untimely
  Budgeting was inadequate
  Corrective control was not exercised in time
  Input price changes occurred
Chapter 11-3

## Slide 28: Controlling Time
There are several things that can cause a project’s schedule to require control:
  Technical difficulties took longer than planned to resolve
  Initial time estimates were optimistic
  Task sequencing was incorrect
  Required inputs of material, personnel, or equipment were unavailable when needed
  Necessary preceding tasks were incomplete
  Customer generated change orders required rework
  Governmental regulations were altered
Chapter 11-4

## Slide 29: Purposes of Control
There are two fundamental objectives of control:
  1. The regulation of results through the alteration of activities
  2. The stewardship of organizational assets
The project manager needs to be equally attentive to both regulation and conservation
The project manager must guard the physical assets of the organization, its human resources, and its financial resources
Chapter 11-5

## Slide 30: Physical Asset Control
Requires control of the use of physical assets
  Concerned with asset maintenance, whether preventive or corrective
  Also the timing of maintenance or replacement as well as the quality of maintenance
  Setting up maintenance schedules in such a way as to keep the equipment in operating condition while minimizing interference to ongoing work
  Physical inventory whether equipment or material must also be controlled
Chapter 11-6

## Slide 31: Human Resource Control
Stewardship of human resources requires controlling and maintaining the growth and development of people
Projects provide fertile ground for cultivating people
Because projects are unique, it is possible for people working on projects to gain a wide range of experience in a reasonably short period of time
Chapter 11-7

## Slide 32: Financial Resource Control
The techniques of financial control, both conservation and regulation, are well known:
  Current asset controls
  Project budgets
  Capital investment controls
These controls are exercised through a series of analyses and audits conducted by the accounting/controller function
Chapter 11-8

## Slide 33: Financial Resource Control
Representation of the accounting/controlling function on the project team is mandatory
The parent organization is responsible for the conservation and proper use of resources owned by the client or charged to the client
Due diligence requires that the organization proposing a project conduct a reasonable investigation, verification, and disclosure of all material facts relevant to the firm’s ability to conduct the project
Chapter 11-9

## Slide 34: Three Types of Control Processes
Decisions must be made concerning:
  At what points in the project will control be exerted
  What is to be controlled
  How it will be measured
  How much deviation will be tolerated
  How to spot and correct potential deviations before they occur
Chapter 11-10

## Slide 35: Three Types of Control Processes
No matter what the purpose in controlling a project there are two basic types of control mechanisms that can be used:
  Go/no-go control
  Post control
Cybernetic control is a third, but less common control mechanism that is rarely directly applicable to projects.
Chapter 11-11

## Slide 36: Go/No-go Controls
Take the form of testing to see if some specific precondition has been met
Most of the control in project management falls into this category
This type of control can be used on almost every aspect of a project
Must exercise judgment in the use of go/no-go controls
Go/no-go controls operate only when and if the controller uses them
Chapter 11-12

## Slide 37: Information Requirements for Go/no-go Controls
The project proposal, plans specifications, schedules and budgets contain all the information needed to apply go/no-go controls to the project
Milestones are the key events that serve as a focus for ongoing control activity
These milestones are the project’s deliverables in the form of in-process output or final output
Chapter 11-13

## Slide 38: Postcontrol
Postcontrols are applied after the fact
Directed toward improving the chances for future projects to meet their goals
It is applied through a relatively formal document that contains four distinct sections:
  The project objectives
  Milestones, checkpoints, and budgets
  The final report on project
  Recommendations for performance and process improvement
Chapter 11-14

## Slide 39: Characteristics of a Control System
A good control system:
  Should be flexible
  Should be cost effective
  Must be truly useful
  Must satisfy the real needs of the project
  Must operate in a timely manner
  Sensors and monitors should be sufficiently accurate and precise to control the project within the limits that are functional for the client and parent organization
Chapter 11-15

## Slide 40: Characteristics of a Control System
A good control system (cont.):
  Should be as simple as possible
  Should be easy to maintain
  Should be capable of being extended or otherwise altered
  Should be fully documented when installed
    the documentation should include a complete training program in system operation
Chapter 11-16

## Slide 41: Control Systems
All control systems use feedback as a control process
The control of performance, cost, and time usually require different input data:
  Performance - engineering change notices, test results, quality checks, rework tickets, scrap rates
  Cost - budgets to actual cash flows, purchase orders, absenteeism, income reports, labor hour charges, accounting variance reports
  Schedule - benchmark reports, status reports, PERT/CPM networks, earned value graphs, Gantt charts, WBS, and action plans
Chapter 11-17

## Slide 42: Control Tools
Some of the most important tools available for the project manager to use in controlling the project are variance analysis and trend projection
A budget plan or expected growth curve of time or cost for a certain task is plotted
Actual values are plotted as a dashed line as the work is actually finished
At each point in time a new projection from the actual data is used to forecast what will occur in the future
Chapter 11-18

## Slide 43: Control Tools
Trend projection
Chapter 11-19

## Slide 44: Critical Ratio Control Charts
The critical ratio is made up of two parts:
  The ratio of actual progress to scheduled progress
  The ratio of budgeted cost to actual cost
The critical ratio is a good measure of the general health of the project
By combining two ratios, it weighs them equally, allowing a “bad” ratio to be offset by a “good” ratio
Chapter 11-20

## Slide 45: Critical Ratio
Chapter 11-21
Task
Number
Critcal
Ratio
Actual
Cost
Budgeted
Cost
Scheduled
Progress
Actual
Progress
1 (2 / 3) X (6 / 4) = 1.0
2 (2 / 3) X (6 / 6) = .67
3 (3 / 3) X (4 / 6) = .67
4 (3 / 2) X (6 / 6) = 1.5
5 (3 / 3) X (6 / 4) = 1.5

## Slide 46: Critical Ratio
Critical ratio control chart
Chapter 11-22

## Slide 47: Benchmarking
A recent addition to the arsenal of of project control tools is benchmarking
Benchmarking makes comparisons to “best in class” practices across organizations
Some successful organizations have been benchmarked on their best practices and key success factors for projects being conducted in functional organizations
Chapter 11-23

## Slide 48: Best Practices and Keys to Success
There were four major areas found to help projects in functional organizations:
  Promoting the benefits of project management
  Personnel pay for project management skills and high risk projects through bonuses, stock options, and other incentives
  Methodology
  Results of project management
Chapter 11-24

## Slide 49: Control as a Function of Management
The purpose of controlling is always the same: to bring the actual schedule, budget, and deliverables of the project into reasonably close congruence with the planned schedule, budget, and deliverables
The job of the project manager is to set controls that will encourage those behaviors that are deemed desirable and discourage those that are not
Chapter 11-25

## Slide 50: Cybernetic Controls
Human response to steering controls tends to be positive
Steering controls are usually viewed as helpful rather than a source of unwelcome pressure
Response to steering controls also depends on the acceptance that the goals of the control system are appropriate
Chapter 11-26

## Slide 51: Go/No-go Controls
Response to go/no-go controls tends to be neutral or negative
“Barely good enough” results are just as acceptable as “perfect” results
The system makes it difficult for the worker to take pride in high quality work because the system does not recognize gradations of quality
The fact that this kind of control emphasizes “good enough” performance is no excuse for the nonchalant application of careless standards
Chapter 11-27

## Slide 52: Postcontrols
Postcontrols are seen as much the same as a report card
They may serve as the basis for reward or punishment, but they are received too late to change current performance
Because postcontrols are placed on the process of conducting a project, they may be applied to such areas as: communication, cooperation, quality of project management, and the nature of interaction with the client
Chapter 11-28

## Slide 53: Balance in a Control System
General features of a balanced control system:
  Built with cognizance of the fact that investment in control is subject to sharply diminishing returns
  Recognizes that as control increases past some point, innovative activity is more and more damped, and then finally shut off completely
  Directed toward the correction of error rather than toward punishment
  Exerts control only to the degree required to achieve its objectives
  Utilizes the lowest degree of hassle consistent with accomplishing its goals
Chapter 11-29

## Slide 54: Control of Creative Activities
The more creativity involved, the greater the degree of uncertainty surrounding outcomes
Too much control tends to inhibit creativity
Control is not necessarily the enemy of creativity, nor does creative activity imply complete uncertainty of
There are three general approaches to control creative projects:
  Progress review
  Personnel reassignment
  Control of input resources
Chapter 11-30

## Slide 55: Progress Review
The progress review focuses on the process of reaching outcomes rather than on the outcomes per se
The process is controllable even if the precise results are not
Control should be instituted at each project milestone
The object of control is to ensure that the research design is sound and is being carried out as planned or amended
Chapter 11-31

## Slide 56: Personnel Reassignment
This type of control is straightforward - individuals who are productive are kept
Those who are not, are moved to other jobs or to other organizations
While it is not difficult to identify those who fall in the top and bottom quartiles, it is usually quite hard to make clear distinctions between the people in the middle quartiles
Chapter 11-32

## Slide 57: Control of Input Resources
The focus is on efficiency
The ability to manipulate input resources carries with it considerable control over output
Considerable resource expenditure may occur with no visible results, but suddenly many outcomes may be delivered
The milestones for application of resource control must be chosen with great care
Chapter 11-33

## Slide 58: Control of Change and Scope Creep
Coping with changes and changing priorities is perceived as the most important single problem facing the project manager
The most common changes are due to the natural tendency of the client and project team members to try to improve the product or service
The later these changes are made in the project, the more difficult and costly they are to complete
Without control, a continuing accumulation of little changes can have a major negative impact on the project’s schedule and cost
Chapter 11-34
Notes: Many projects suffer from scope creep, which is the tendency for the project scope to expand over time—usually by changing requirements, specifications, and priorities. Scope creep can be reduced by carefully writing your scope statement.
A scope statement that is too broad is an invitation for scope creep. Scope creep can have a positive or negative effect on the project, but in most cases scope creep means added costs and possible project delays. Changes in requirements, specifications, and priorities frequently result in cost overruns and delays. Examples are abundant—Denver airport baggage handling system; Boston’s new freeway system. (“The Big Dig”); China’s fast train in Shanghai; and the list goes on. On software development projects, scope creep is manifested in bloated products in which added functionality undermines ease of use. If the project scope needs to change, it is critical to have a sound change control process in place that records the change and keeps a log of all project changes. The log identifies the change, impact, and those responsible for accepting or rejecting a proposed change. Project managers in the field constantly suggest that dealing with changing requirements is one of their most perplexing problems.

## Slide 59: Control of Change and Scope Creep
The project manager’s best hope is to control the process by which change is introduced and accomplished
This can be done with a formal change control system that is able to:
  Review all requested changes and identify all task impacts
  Translate those impacts into project performance, cost, and schedule
  Evaluate the benefits and costs of the requested changes
  Accept or reject the changes and communicate to all concerned parties
  Ensure that changes are implemented properly
Chapter 11-35

## Slide 60: Effective Change Control Procedure
The following guidelines, applied with reasonable rigor, can be used to effectively control changes:
  1. All project contracts or agreements must include a description of how requests for a change in the project’s plan, budget, schedule, and/or deliverables, will be introduced and processed.
  2. Any change in a project will be in the form of a change order that will include a description of the agreed-upon change together with any changes in the plan, budget, schedule, and/or deliverables that result from the change.
Chapter 11-36

## Slide 61: Effective Change Control Procedure
  3. Changes must be approved, in writing, by the client’s agent as well as by an appropriate representative of senior management of the firm responsible for carrying out the project.
  4. The project manager must be consulted on all desired changes prior to the preparation and approval of the change order. The project manager’s approval, however, is not required.
  5. Once the change order has been completed and approved, the project master plan should be amended to reflect the change, and the change order becomes part of the master plan.
Chapter 11-37